## Sheet1
Budget
The WBS dictionary contains all the details of the WBS necessary to successfully complete the project. Most importantly, it contains a definition of each work package, which can be thought of as a mini scope statement. Resources on the project will look at the WBS dictionary to determine the scope of the work package they have been assigned, so it is important to be clear when writing the definition. Most WBS dictionaries contain more information than we show in our sample. These things usually include Level of Effort, Cost Control Numbers, Resource Assignments, and Responsibility Assignments, just to name a few.
WBS Code | Task Name | Resource Name | Work Estimate Days | Labor Hours | Labor Rates | Total Labor | Reserve | Equipment | Estimate
1 | Overall Project
1.1 | Project Management
1.1.1 | Manage Project | Chris Johnson (Project Manager) | 127 | 1016 | 75 | 76200 |  |  | 76200
1.2 | System Requirements |  |  | 0
1.2.1 | Gather Business Requirements | Ryan Neff (Functional Lead) | 8 | 64 | 75 | 4800 |  |  | 4800
|  | Stacy Lyle (Functional Analyst) |  | 0 | 75 | 0 |  |  | 0
1.2.2 | Design Business Process Flows | Ryan Neff (Functional Lead) | 4 | 32 | 75 | 2400 |  |  | 2400
|  | Stacy Lyle (Functional Analyst) |  | 0
1.2.3 | Finalize Technical Requirements | Rick Burke (Infrastructure Lead) | 6 | 48 | 75 | 3600 |  |  | 3600
1.2.4 | Create Operational Requirements | Ryan Neff (Functional Lead) | 15 | 120 | 75 | 9000 |  |  | 9000
|  | Stacy Lyle (Functional Analyst) |  | 0
|  | Rick Burke (Infrastructure Lead) |  | 0
1.2.5 | Identify Technical Infrastructure Needs | Rick Burke (Infrastructure Lead) | 2 | 16 | 75 | 1200 |  |  | 1200
1.3 | Software Requirements |  |  | 0
1.3.1 | Create Functional Requirements |  |  | 0
1.3.1.1 | Capture Customer Profile | Ryan Neff (Functional Lead) | 4 | 32 | 75 | 2400 |  |  | 2400
1.3.1.2 | View and Search Product Catalog | Ryan Neff (Functional Lead) | 6 | 48 | 75 | 3600 |  |  | 3600
1.3.1.3 | Updating and Calculating Shopping Cart | Ryan Neff (Functional Lead) | 3 | 24 | 75 | 1800 |  |  | 1800
1.3.1.4 | Taking Payments | Stacy Lyle (Functional Analyst) | 6 | 48 | 75 | 3600 |  |  | 3600
1.3.1.5 | Submit Order | Ryan Neff (Functional Lead) | 4 | 32 | 75 | 2400 |  |  | 2400
1.3.1.6 | Check Order History & Order Status | Ryan Neff (Functional Lead) | 3 | 24 | 75 | 1800 |  |  | 1800
1.3.2 | Create Data Requirements | Stacy Lyle (Functional Analyst) | 3 | 24 | 75 | 1800 |  |  | 1800
1.3.3 | Create ERP Interface Requirements | Stacy Lyle (Functional Analyst) | 7 | 56 | 75 | 4200 |  |  | 4200
1.3.4 | Create User Interface Requirements | Stacy Lyle (Functional Analyst) | 4 | 32 | 75 | 2400 |  |  | 2400
1.4 | Detailed Design |  |  | 0
1.4.1 | Design Capture Customer Profile Pages & Components | Marc Sanders (Development Lead) | 13.5 | 108 | 75 | 8100 |  |  | 8100
|  | Ryan Neff (Functional Lead) [50%] |  | 0 | 75 | 0 |  |  | 0
1.4.2 | Design View and Search Product Catalog Pages & Components | Developer 1 (TBD) | 13.5 | 108 | 165 | 17820 |  |  | 17820
|  | Ryan Neff (Functional Lead) [50%] |  | 0 | 75 | 0 |  |  | 0
1.4.3 | Design Updating and Calculating Shopping Cart | Developer 1 (TBD) | 6 | 48 | 165 | 7920 |  |  | 7920
|  | Ryan Neff (Functional Lead) [50%] |  | 0 | 75 | 0 |  |  | 0
1.4.4 | Design Taking Payments Pages & Components | Marc Sanders (Development Lead) | 6 | 48 | 75 | 3600 |  |  | 3600
|  | Stacy Lyle (Functional Analyst) |  | 0 | 75 | 0 |  |  | 0
1.4.5 | Design Submit Order Pages & Components | Marc Sanders (Development Lead) | 8 | 64 | 75 | 4800 |  |  | 4800
|  | Ryan Neff (Functional Lead) |  | 0 | 75 | 0 |  |  | 0
1.4.6 | Design Check Order History & Order Status Pages & Components | Marc Sanders (Development Lead) | 4 | 32 | 75 | 2400 |  |  | 2400
|  | Ryan Neff (Functional Lead) |  | 0 | 75 | 0 |  |  | 0
1.4.7 | Design Logical & Physical Data Model | Sanjay Vohra (DBA) | 18 | 144 | 75 | 10800 |  |  | 10800
|  | Stacy Lyle (Functional Analyst) |  | 0 | 75 | 0 |  |  | 0
1.4.8 | Design ERP Interface | Developer 1 (TBD) | 20 | 160 | 165 | 26400 |  |  | 26400
|  | Stacy Lyle (Functional Analyst) |  | 0 | 75 | 0 |  |  | 0
1.5 | Test Planning |  |  | 0
1.5.1 | Gather Testing Requirements | Kara Siposki (Test Lead) | 14 | 112 | 75 | 8400 |  |  | 8400
|  | Todd Eliason (Tester) |  | 0 | 75 | 0 |  |  | 0
1.5.2 | Create System Test Plan & Test Cases | Kara Siposki (Test Lead) | 20 | 160 | 75 | 12000 |  |  | 12000
|  | Todd Eliason (Tester) |  | 0 | 75 | 0 |  |  | 0
1.5.3 | Write System Test Scripts | Kara Siposki (Test Lead) | 22 | 176 | 75 | 13200 |  |  | 13200
|  | Todd Eliason (Tester) |  | 0 | 75 | 0 |  |  | 0
1.6 | Technical Infrastructure |  |  | 0 |  |  |  | 98500 | 98500
1.6.1 | Create Development Environment | Rick Burke (Infrastructure Lead) | 20 | 160 | 75 | 12000 |  |  | 12000
1.6.2 | Create Testing Environment | Rick Burke (Infrastructure Lead) [90%] | 34.2 | 273.6 | 75 | 18468 |  |  | 18468
1.6.3 | Support Development Environment | Rick Burke (Infrastructure Lead) [10%] | 3.8 | 30.4 | 75 | 228 |  |  | 228
1.6.4 | Support Testing Environment & Deployment | Rick Burke (Infrastructure Lead) | 46 | 368 | 75 | 27600 |  |  | 27600
1.6.5 | Support Database | Sanjay Vohra (DBA) [10%] | 4.6 | 36.8 | 75 | 276 |  |  | 276
1.7 | Development & Unit Test |  |  | 0
1.7.1 | Build Capture Customer Profile Pages & Components | Developer 2 (TBD) | 13 | 104 | 165 | 17160 |  |  | 17160
1.7.2 | Build View and Search Product Catalog Pages & Components | Developer 3 (TBD) | 12 | 96 | 165 | 15840 |  |  | 15840
1.7.3 | Build Updating and Calculating Shopping Cart | Developer 3 (TBD) | 7 | 56 | 165 | 9240 |  |  | 9240
1.7.4 | Build Promotional Bundles | Marc Sanders (Development Lead) | 15 | 120 | 500 | 60000 |  |  | 60000
|  | Consultant | 3 | 24 | 500 | 12000 |  |  | 12000
1.7.5 | Build Taking Payments Pages & Components | Developer 2 (TBD) | 8 | 64 | 165 | 10560 |  |  | 10560
1.7.6 | Build Submit Order Pages & Components | Developer 2 (TBD) | 12 | 96 | 165 | 15840 |  |  | 15840
|  | Developer 3 (TBD) | 12 | 192 | 165 | 31680 |  |  | 31680
1.7.7 | Build Check Order History & Order Status Pages & Components | Marc Sanders (Development Lead) | 6 | 48 | 75 | 3600 |  |  | 3600
1.7.8 | Build Logical & Physical Data Model | Sanjay Vohra (DBA) [50%] | 15.5 | 124 |  | 0
1.7.9 | Build ERP Interface | Developer 1 (TBD) | 18 | 144 | 165 | 23760 |  |  | 23760
1.7.10 | Support Development & Assembly Test | Ryan Neff (Functional Lead) | 46 | 368 | 75 | 27600 |  |  | 27600
|  | Stacy Lyle (Functional Analyst) |  | 0 | 75 | 0 |  |  | 0
1.8 | Testing |  |  | 0
1.8.1 | Perform Assembly Testing |  |  | 0
1.8.1.1 | Perform Phase 1 Testing | Marc Sanders (Development Lead) | 12 | 96 | 75 | 7200 |  |  | 7200
1.8.1.2 | Perform Phase 2 Testing | Marc Sanders (Development Lead) | 45 | 360 | 75 | 27000 |  |  | 27000
|  | Developer 1 (TBD) | 45 | 360 | 165 | 59400 |  |  | 59400
|  | Developer 2 (TBD) | 45 | 360 | 165 | 59400 |  |  | 59400
|  | Developer 3 (TBD) | 45 | 360 | 165 | 59400 |  |  | 59400
1.8.2 | Perform System Testing | Kara Siposki (Test Lead) | 160 | 1280 | 75 | 96000 |  |  | 96000
|  | Todd Eliason (Tester) | 160 | 1280 | 75 | 96000 |  |  | 96000
|  | Marc Sanders (Development Lead) | 160 | 1280 | 75 | 96000 |  |  | 96000
|  | Developer 1 (TBD) | 160 | 1280 | 165 | 211200 |  |  | 211200
|  | Developer 2 (TBD) | 160 | 1280 | 165 | 211200 |  |  | 211200
|  | Developer 3 (TBD) | 160 | 1280 | 165 | 211200 |  |  | 211200
|  | Ryan Neff (Functional Lead) | 160 | 1280 | 75 | 96000 |  |  | 96000
|  | Stacy Lyle (Functional Analyst) | 160 | 1280 | 75 | 96000 |  |  | 96000
1.8.3 | Perform Validation Testing | Kara Siposki (Test Lead) | 80 | 640 |  | 0
|  | Todd Eliason (Tester) | 80 | 640 | 75 | 48000 |  |  | 48000
|  | Marc Sanders (Development Lead) | 80 | 640 | 75 | 48000 |  |  | 48000
|  | Developer 1 (TBD) | 80 | 640 | 165 | 105600 |  |  | 105600
|  | Developer 2 (TBD) | 80 | 640 | 165 | 105600 |  |  | 105600
|  | Developer 3 (TBD) | 80 | 640 | 165 | 105600 |  |  | 105600
|  | Ryan Neff (Functional Lead) | 80 | 640 | 75 | 48000 |  |  | 48000
|  | Stacy Lyle (Functional Analyst) | 80 | 640 | 75 | 48000 |  |  | 48000
1.9 | Deployment |  |  | 0
1.9.1 | Implement System | Kara Siposki (Test Lead), Todd Eliason (Tester), Marc Sanders (Development Lead), Developer 1 (TBD), Developer 2 (TBD), Developer 3 (TBD), Ryan Neff (Functional Lead), Stacy Lyle (Functional Analyst) | 80 | 640 | 75 | 48000 |  |  | 48000
|  | Todd Eliason (Tester) | 80 | 640 | 75 | 48000 |  |  | 48000
|  | Marc Sanders (Development Lead) | 80 | 640 | 75 | 48000 |  |  | 48000
|  | Developer 1 (TBD) | 80 | 640 | 165 | 105600 |  |  | 105600
|  | Developer 2 (TBD) | 80 | 640 | 165 | 105600 |  |  | 105600
|  | Developer 3 (TBD) | 80 | 640 | 165 | 105600 |  |  | 105600
|  | Ryan Neff (Functional Lead) | 80 | 640 | 75 | 48000 |  |  | 48000
|  | Stacy Lyle (Functional Analyst) | 80 | 640 | 75 | 48000 |  |  | 48000
1.9.2 | Deploy To Production | Kara Siposki (Test Lead) | 8 | 64 | 75 | 4800 |  |  | 4800
|  | Todd Eliason (Tester) | 80 | 640 | 75 | 48000 |  |  | 48000
|  | Marc Sanders (Development Lead) | 80 | 640 | 75 | 48000 |  |  | 48000
|  | Developer 1 (TBD) | 80 | 640 | 165 | 105600 |  |  | 105600
|  | Developer 2 (TBD) | 80 | 640 | 165 | 105600 |  |  | 105600
|  | Developer 3 (TBD) | 80 | 640 | 165 | 105600 |  |  | 105600
|  | Ryan Neff (Functional Lead) | 80 | 640 | 75 | 48000 |  |  | 48000
|  | Stacy Lyle (Functional Analyst) | 80 | 640 | 75 | 48000 |  |  | 48000
1.9.3 | Project Wrap-Up | Kara Siposki (Test Lead) | 8 | 64 | 75 | 4800 |  |  | 4800
|  | Todd Eliason (Tester) | 80 | 640 | 75 | 48000 |  |  | 48000
|  | Marc Sanders (Development Lead) | 80 | 640 | 75 | 48000 |  |  | 48000
|  | Developer 1 (TBD) | 80 | 640 | 165 | 105600 |  |  | 105600
|  | Developer 2 (TBD) | 80 | 640 | 165 | 105600 |  |  | 105600
|  | Developer 3 (TBD) | 80 | 640 | 165 | 105600 |  |  | 105600
|  | Ryan Neff (Functional Lead) | 80 | 640 | 75 | 48000 |  |  | 48000
|  | Stacy Lyle (Functional Analyst) | 80 | 640 | 75 | 48000 |  |  | 48000