## Sheet1
WBS Dictionary
The WBS dictionary contains all the details of the WBS necessary to successfully complete the project. Most importantly, it contains a definition of each work package, which can be thought of as a mini scope statement. Resources on the project will look at the WBS dictionary to determine the scope of the work package they have been assigned, so it is important to be clear when writing the definition. Most WBS dictionaries contain more information than we show in our sample. These things usually include Level of Effort, Cost Control Numbers, Resource Assignments, and Responsibility Assignments, just to name a few.
Task ID | WBS Code | Task Name | Resource Name | Resource Reasoning
1 | 1 | Overall Project
2 | 1.1 | Project Management
3 | 1.1.1 | Manage Project | Chris Johnson (Project Manager) | The project needs an overall project manager to ensure the success of the project and to ensure the project is within budget and finished within the schedule.
4 | 1.2 | System Requirements
5 | 1.2.1 | Gather Business Requirements | Ryan Neff (Functional Lead), Stacy Lyle (Functional Analyst) | To accurately and comprehensively gather business requirements
6 | 1.2.2 | Design Business Process Flows | Ryan Neff (Functional Lead), Stacy Lyle (Functional Analyst) | To accurately and comprehensively design the business process flows
7 | 1.2.3 | Finalize Technical Requirements | Rick Burke (Infrastructure Lead) | To accurately finalize the technical requirements
8 | 1.2.4 | Create Operational Requirements | Ryan Neff (Functional Lead), Stacy Lyle (Functional Analyst), Rick Burke (Infrastructure Lead) | To accurately and comprehensively create the operational requirements
9 | 1.2.5 | Identify Technical Infrastructure Needs | Rick Burke (Infrastructure Lead) | To accurately and comprehensively identify the technical infrastructure
10 | 1.3 | Software Requirements
11 | 1.3.1 | Create Functional Requirements
12 | 1.3.1.1 | Capture Customer Profile | Ryan Neff (Functional Lead) | To accurately and comprehensively create Capture Customer Profile
13 | 1.3.1.2 | View and Search Product Catalog | Ryan Neff (Functional Lead) | To accurately and comprehensively create View and Search Product Cataglog
14 | 1.3.1.3 | Updating and Calculating Shopping Cart | Ryan Neff (Functional Lead) | To accurately and comprehensively create Updating and Calculating Shopping Cart
15 | 1.3.1.4 | Taking Payments | Stacy Lyle (Functional Analyst) | To accurately and comprehensively create Taking Payments
16 | 1.3.1.5 | Submit Order | Ryan Neff (Functional Lead) | To accurately and comprehensively create Submit Order
17 | 1.3.1.6 | Check Order History & Order Status | Ryan Neff (Functional Lead) | To accurately and comprehensively create Check Order History and Order Status
18 | 1.3.2 | Create Data Requirements | Stacy Lyle (Functional Analyst) | To accurately create Data Requirements
19 | 1.3.3 | Create ERP Interface Requirements | Stacy Lyle (Functional Analyst) | To accurately create ERP Interface Requirements
20 | 1.3.4 | Create User Interface Requirements | Stacy Lyle (Functional Analyst) | To accurately create User Interface Requirements
21 | 1.4 | Detailed Design
22 | 1.4.1 | Design Capture Customer Profile Pages & Components | Marc Sanders (Development Lead), Ryan Neff (Functional Lead) [50%] | To sufficiently and excellently design Capture Customer Profile Pages & Components
23 | 1.4.2 | Design View and Search Product Catalog Pages & Components | Developer 1 (TBD), Ryan Neff (Functional Lead) [50%] | To sufficiently and excellently design View and Search Product Catalog Pages & Components
24 | 1.4.3 | Design Updating and Calculating Shopping Cart | Developer 1 (TBD), Ryan Neff (Functional Lead) | To sufficiently and excellently design Updating and Calculating Shopping Cart
25 | 1.4.4 | Design Taking Payments Pages & Components | Marc Sanders (Development Lead), Stacy Lyle (Functional Analyst) | To sufficiently and excellently design Taking Payments Pages & Components
26 | 1.4.5 | Design Submit Order Pages & Components | Marc Sanders (Development Lead), Ryan Neff (Functional Lead) | To sufficiently and excellently design Submit Order Pages & Components
27 | 1.4.6 | Design Check Order History & Order Status Pages & Components | Marc Sanders (Development Lead), Ryan Neff (Functional Lead) | To sufficiently and excellently design Check Order & Order Status Pages & Components
28 | 1.4.7 | Design Logical & Physical Data Model | Sanjay Vohra (DBA), Stacy Lyle (Functional Analyst) | To sufficiently and excellently design Logical & Physical Data Model
29 | 1.4.8 | Design ERP Interface | Developer 1 (TBD), Stacy Lyle (Functional Analyst) | To sufficiently and excellently design ERP Interface
30 | 1.5 | Test Planning
31 | 1.5.1 | Gather Testing Requirements | Kara Siposki (Test Lead), Todd Eliason (Tester) | To accurately gather testing requirements
32 | 1.5.2 | Create System Test Plan & Test Cases | Kara Siposki (Test Lead), Todd Eliason (Tester) | To comprehensilvey create system test plan & test cases
33 | 1.5.3 | Write System Test Scripts | Kara Siposki (Test Lead), Todd Eliason (Tester) | To accurately and comprehensively write system test scripts
34 | 1.6 | Technical Infrastructure
35 | 1.6.1 | Create Development Environment | Rick Burke (Infrastructure Lead) | To sufficiently create a development environment
36 | 1.6.2 | Create Testing Environment | Rick Burke (Infrastructure Lead) [90%] | To sufficiently create a testing environment
37 | 1.6.3 | Support Development Environment | Rick Burke (Infrastructure Lead) [10%] | To adequately support the development environment
38 | 1.6.4 | Support Testing Environment & Deployment | Rick Burke (Infrastructure Lead) | To adequately support testing environment & deployment
39 | 1.6.5 | Support Database | Sanjay Vohra (DBA) [10%] | To adequately support database
40 | 1.7 | Development & Unit Test
41 | 1.7.1 | Build Capture Customer Profile Pages & Components | Developer 2 (TBD) | To accurately and comprehensively build Capture Customer Profile Pages & Components
42 | 1.7.2 | Build View and Search Product Catalog Pages & Components | Developer 3 (TBD) | To accurately and comprehensively build View and Search Product Catalog Pages & Components
43 | 1.7.3 | Build Updating and Calculating Shopping Cart | Developer 3 (TBD) | To accurately and comprehensively build Updating and Calculating Shopping Cart
44 | 1.7.4 | Bulid Promotional Bundles | Marc Sanders (Development Lead), Consultant | To accurately and comprehensively build Promotional Bundles
45 | 1.7.5 | Build Taking Payments Pages & Components | Developer 2 (TBD) | To accurately and comprehensively build Taking Payments Pages & Components
46 | 1.7.6 | Build Submit Order Pages & Components | Developer 2 (TBD), Developer 3 (TBD) | To accurately and comprehensively build Submit Order Pages & Components
47 | 1.7.7 | Build Check Order History & Order Status Pages & Components | Marc Sanders (Development Lead) | To accurately and comprehensively build Check Order History & Order Status Pages & Components
48 | 1.7.8 | Build Logical & Physical Data Model | Sanjay Vohra (DBA) [50%] | To accurately and comprehensively build Logical & Physical Data Model
49 | 1.7.9 | Build ERP Interface | Developer 1 (TBD) | To accurately and comprehensively build ERP Interface
50 | 1.7.10 | Support Development & Assembly Test | Ryan Neff (Functional Lead), Stacy Lyle (Functional Analyst) | To adequately support development & assembly test
51 | 1.8 | Testing
52 | 1.8.1 | Perform Assembly Testing
53 | 1.8.1.1 | Perform Phase 1 Testing | Marc Sanders (Development Lead) | To adequately test Phase 1
54 | 1.8.1.2 | Perform Phase 2 Testing | Marc Sanders (Development Lead), Developer 1 (TBD), Developer 2 (TBD), Developer 3 (TBD) | To adequately test Phase 2
55 | 1.8.2 | Perform System Testing | Kara Siposki (Test Lead), Todd Eliason (Tester), Marc Sanders (Development Lead), Developer 1 (TBD), Developer 2 (TBD), Developer 3 (TBD), Ryan Neff (Functional Lead), Stacy Lyle (Functional Analyst) | To adequately testing the system
56 | 1.8.3 | Perform Validation Testing | Kara Siposki (Test Lead), Todd Eliason (Tester), Marc Sanders (Development Lead), Developer 1 (TBD), Developer 2 (TBD), Developer 3 (TBD), Ryan Neff (Functional Lead), Stacy Lyle (Functional Analyst) | To adequately test validation
57 | 1.9 | Deployment
58 | 1.9.1 | Implement System | Kara Siposki (Test Lead), Todd Eliason (Tester), Marc Sanders (Development Lead), Developer 1 (TBD), Developer 2 (TBD), Developer 3 (TBD), Ryan Neff (Functional Lead), Stacy Lyle (Functional Analyst) | To adequately and successfully implement system
59 | 1.9.2 | Deploy To Production | Kara Siposki (Test Lead), Todd Eliason (Tester), Marc Sanders (Development Lead), Developer 1 (TBD), Developer 2 (TBD), Developer 3 (TBD), Ryan Neff (Functional Lead), Stacy Lyle (Functional Analyst) | To adequately and successfully deploy to production
60 | 1.9.3 | Project Wrap-Up | Kara Siposki (Test Lead), Todd Eliason (Tester), Marc Sanders (Development Lead), Developer 1 (TBD), Developer 2 (TBD), Developer 3 (TBD), Ryan Neff (Functional Lead), Stacy Lyle (Functional Analyst), Rick Burke (Infrastructure Lead) | To comprehensively wrap up project