## Sheet1
WBS Dictionary
| The WBS dictionary contains all the details of the WBS necessary to successfully complete the project. Most importantly, it contains a definition of each work package, which can be thought of as a mini scope statement. Resources on the project will look at the WBS dictionary to determine the scope of the work package they have been assigned, so it is important to be clear when writing the definition. Most WBS dictionaries contain more information than we show in our sample. These things usually include Level of Effort, Cost Control Numbers, Resource Assignments, and Responsibility Assignments, just to name a few. |  | 2
Task ID | WBS Code | Task Name | Task Description | Work Estimate Days | Predecessors
1 | 1 | Overall Project | All work applicable to develop and deploy final product
2 | 1.1 | Project Management | Management necessary to manage project
3 | 1.1.1 | Manage Project | Manage the project | 127 | 59FF
4 | 1.2 | System Requirements | All system requirements necessary for the project
5 | 1.2.1 | Gather Business Requirements | List and gather out all of the business requirements | 8
6 | 1.2.2 | Design Business Process Flows | Analyze all of the process flow of each department in the business and design it | 4 | 5
7 | 1.2.3 | Finalize Technical Requirements | Review and finalize the technical requirements | 6
8 | 1.2.4 | Create Operational Requirements | Based on the business requirements and process flows, create the operational requirements | 15 | 5, 6
9 | 1.2.5 | Identify Technical Infrastructure Needs | Review the techinical and operational requirements to identify the technical infrastrucure needs | 2 | 7, 8
10 | 1.3 | Software Requirements | All software requirements necessary for the project
11 | 1.3.1 | Create Functional Requirements | Based on the business requirements, process flows, and operational requirements, create the functional requirements |  | 5, 6, 8
12 | 1.3.1.1 | Capture Customer Profile | Create functional feature that captures customer profile | 4
13 | 1.3.1.2 | View and Search Product Catalog | Create functional feature that can view and search product catalog | 6
14 | 1.3.1.3 | Updating and Calculating Shopping Cart | Create functional feature that updates and calculates shopping cart | 3 | 13
15 | 1.3.1.4 | Taking Payments | Create functional feature that will take payments | 6
16 | 1.3.1.5 | Submit Order | Create functionnal freature for submission of orders | 4 | 12, 13, 14, 15
17 | 1.3.1.6 | Check Order History & Order Status | Create functional feature to allow customers to check order histroy and order status | 3 | 16
18 | 1.3.2 | Create Data Requirements | Create the data requirements for the software | 3 | 12, 13
19 | 1.3.3 | Create ERP Interface Requirements | Create the ERP Interface requirements for the software | 7 | 16SS
20 | 1.3.4 | Create User Interface Requirements | Create the User Interface requiremennts for the software | 4 | 11SS
21 | 1.4 | Detailed Design | All detailed designs necessary for the project |  | 10
22 | 1.4.1 | Design Capture Customer Profile Pages & Components | Design Capture Customer Profile Pages & Components for the software | 13.5
23 | 1.4.2 | Design View and Search Product Catalog Pages & Components | Design View and Search Product Catalog Pages & Components for the software | 13.5
24 | 1.4.3 | Design Updating and Calculating Shopping Cart | Design Updating and Calculating Shopping Cart for the software | 6 | 23
25 | 1.4.4 | Design Taking Payments Pages & Components | Design Taking Payments Pages & Components for the software | 6
26 | 1.4.5 | Design Submit Order Pages & Components | Design Submit Order Pages & Components for thee software | 8 | 22, 23, 24, 25
27 | 1.4.6 | Design Check Order History & Order Status Pages & Components | Design Check Order History & Order Status Pages & Components for the software | 4 | 26
28 | 1.4.7 | Design Logical & Physical Data Model | Design Logical & Physical Data Model for the software | 18
29 | 1.4.8 | Design ERP Interface | Design ERP Interface for the software | 20 | 22, 23, 24, 25
30 | 1.5 | Test Planning | All test planning necessar for the project
31 | 1.5.1 | Gather Testing Requirements | List out all testing requirements | 14 | 11
32 | 1.5.2 | Create System Test Plan & Test Cases | Create the system test plan and its test cases | 20 | 31, 21
33 | 1.5.3 | Write System Test Scripts | Write the system test scripts | 22 | 32
34 | 1.6 | Technical Infrastructure | All technical infrastructure necessary for the project
35 | 1.6.1 | Create Development Environment | Create the development environment for the developers | 20 | 9
36 | 1.6.2 | Create Testing Environment | Create the testing environment for the developers | 34.2 | 35
37 | 1.6.3 | Support Development Environment | Support the created development environment | 3.8 | 35
38 | 1.6.4 | Support Testing Environment & Deployment | Support the created testing environment and deployment | 46 | 36
39 | 1.6.5 | Support Database | Support the database of the system | 4.6 | 47
40 | 1.7 | Development & Unit Test | All development and unit testing necessary for the project |  | 35
41 | 1.7.1 | Build Capture Customer Profile Pages & Components | Build the capture customer profile pages and components for the software | 13 | 22
42 | 1.7.2 | Build View and Search Product Catalog Pages & Components | Build View and Search Product Catalog Pages & Components for the software | 12 | 23
43 | 1.7.3 | Build Updating and Calculating Shopping Cart | Build Updating and Calculating Shopping Cart for the software | 7 | 24, 42
44 | 1.7.4 | Build Promotional Bundles | Building Promotional Bundles for the software | 15 | 43
45 | 1.7.5 | Build Taking Payments Pages & Components | Build Taking Payments Pages & Components for the software | 6 | 25
46 | 1.7.6 | Build Submit Order Pages & Components | Build Submit Order Pages & Components for the software | 12 | 26, 41, 42, 43, 44
47 | 1.7.7 | Build Check Order History & Order Status Pages & Components | Build Check Order History & Order Status Pages & Components for the software | 6 | 27
48 | 1.7.8 | Build Logical & Physical Data Model | Build Logical & Physical Data Model for the software | 15.5 | 28
49 | 1.7.9 | Build ERP Interface | Build ERP Interface for the software | 18 | 29
50 | 1.7.10 | Support Development & Assembly Test | Support the development and assembly test of the software | 46 | 21
51 | 1.8 | Testing | All testing necessary for the project
52 | 1.8.1 | Perform Assembly Testing | Test assembly of the software |  | 31
53 | 1.8.1.1 | Perform Phase 1 Testing | Test phase 1 | 12 | 41, 42, 43
54 | 1.8.1.2 | Perform Phase 2 Testing | Test phase 2 | 45 | 44, 45, 46, 52 47, 48
55 | 1.8.2 | Perform System Testing | Test the system | 160 | 51, 32, 33
56 | 1.8.3 | Perform Validation Testing | Test the validation of the system | 80 | 54
57 | 1.9 | Deployment | All deployment necessary for the project |  | 50
58 | 1.9.1 | Implement System | Implement the entire system for preparation to deploy | 80
59 | 1.9.2 | Deploy To Production | Deploy the software | 8 | 57
60 | 1.9.3 | Project Wrap-Up | Close all tasks of the project and gather feedback of the performance of the entire project development, complete all paperwork, release resources, archive documents | 90 | 58